## Sheet1
Activity Schedule on site - Template
From | To | Activity | Remarks
1 week before event
|  | Visit to Training and Warm-up venues | LOC, TDs, European Athletics
|  | Visit to Competition Venue and Supporting facilities | LOC, TDs, European Athletics
|  | Timetable Meeting (TDs & Competition Management) | LOC, TDs, European Athletics
|  | Team Hotels Tour (Teams Services once Info Desk is open) | LOC, European Athletics
|  | Preparation Technical Meeting | TDs, European Athletics, LOC
|  | Bibs printing (when EA responsbility) | European Athletics
Days before the event
after final confirmation if needed |  | General Timetable Meeting (All) & Clean Infield Meeting | LOC, TDs, European Atheltics, EP, EBU/HB
day before opening |  | TIC Briefing | TDs, European Athletics, LOC (TIC Mananger)
day before opening |  | Visit to Training and Warm-up venues (Final Check before opening) | TDs, MD, European Athletics, LOC
day before the visit to course |  | Declaration Inspection of Road Events Courses | LOC
day before competition day |  | Visit to Road Races Courses | TDs, MD, European Athletics, LOC
|  | Inspection of the Medical Facilities (All venues incl. Main Medical Center) | MD, European Athletics, LOC
|  | Inspection of the Doping Control Station for blood | DCD, European Athletics, LOC
after the venue inspection |  | Collection of questions for Technical Meeting & Finalise T. Meeting | LOC, European Athletics, TDs
|  | Meeting with Officials (TDs presence tbc with LOC) | LOC, TDs
before test event |  | Call Room Briefing | TDs, European Athletics, LOC (Call Room Mananger)
before 1st competition day |  | Briefing with Combined Events Referee | TDs, European Athletics, LOC
Transponder training
Data Entry Validation Training with STS
Training for volunteers in charge of Starting blocks
Video Screen operator Training
J-2 |  | Final Confirmation Deadline (Day 1) | European Athletics, TIC Manager
J-1
|  | Visit to Competition Venue and Supporting facilities (Final Check) | LOC, TDs, European Athletics
|  | EDM Training with OMEGA | LOC, OMEGA
|  | Photo Finish Judge Training with OMEGA | LOC, OMEGA
|  | Meeting IS, Local Team and OMEGA | OMEGA, LOC Officials, IS
|  | Meeting IPFJ, NPFJ and OMEGA | OMEGA, LOC Officials, IPFJ
|  | Inspection of competition venue for Team Leaders | LOC
From | To | Activity | Remarks
1 day before respective competition day |  | Inspection of Road Races Course | LOC, Road Race Measurer
|  | Official training at competition venue | LOC
within the official training |  | Training with Official Starters | LOC, International Starter
after the technical meeting |  | Meeting Jury of Appeal & Secretary of the JA | JA, JA Secretary, EA
before the rehearsal |  | Meeting International Officials | Int Officials, TDs, European Athletics
(when possible J.2) |  | Rehearsal Event | All
day before the RW event |  | Race Walking Judges Meeting | (IRWJ, Recorder, RW Judge Assistant)
|  | Technical Meeting | TDs, European Athletics, LOC
after the TMeeting, same venue |  | Medical Meeting | MD, DCD European Athletics, LOC
before each Throws event day |  | Personal Implements collection | TIC, Technical Manager
Competition Day 1
|  | Final Confirmation Deadline (Day 2) and everyday for the following day | European Athletics, TIC Manager
after the evening session |  | Debriefing TDs/ITOs, IS, IPFJ | TDs, Int Officials
after the evening session |  | Debriefing TDs / LOC Competition Management and every day | TDs, LOC Competition Management
before each Throws event day |  | Personal Implements collection (and every day before a Throws event day) | TIC
Competition Day 2 & 3
as needed |  | Daily Meeting with the Team Leaders (and subsequent days as needed) | TDs, LOC Comp & Team Services